ISOMO VOICE AI PILOT

Pilot Success Metrics - Board Decision Sheet

Each metric is measured before the pilot (Week 0) and after (Week 6); the change is the result. All instruments are already available to Isomo. Targets are provisional shapes - exact numbers should be locked after the Week-0 baseline is collected.

| # | Metric | What it answers | Instrument | 6-week target | Type |
| --- | --- | --- | --- | --- | --- |
| 1 | Dose delivered | Did students actually practise? (sessions + speaking time) | ElevenLabs logs | >=80% of planned sessions completed; median >=10 of 20 min spent speaking | MUST-HIT |
| 2 | Oral fluency | Did spoken English improve? (the core hypothesis) | DET + SmallTalk2Me | Cohort mean up >=0.5 CEFR sub-level (directional, not certified) | MUST-HIT |
| 3 | Grammar mastery | Did accuracy on taught topics improve? | IXL (already owned) | +15 pts in share of students at SmartScore >=80 | Supporting |
| 4 | Confidence & anxiety | Did students feel more able and less anxious? | Confidence questionnaire (Google Form) | Cohort mean +0.5 (1-5 scale); anxiety subscale falls | MUST-HIT |
| 5 | Equity / dose-response | Do the 25 lowest-baseline (extra-hour) students gain at least as much as the base cohort? | Compare sub-cohort PRE/POST changes | Extra-hour gains >= base-cohort gains | Supporting |
| 6 | Adoption | Is it wanted and scalable, regardless of scores? | End-survey + facilitator debrief | >=75% of students want to continue; facilitators report time freed for higher-order work | Supporting |

Go / No-Go rule for scaling to the Circles

GO if the three MUST-HIT metrics are met (students practised, fluency moved directionally, confidence rose). The three Supporting metrics shape HOW to scale, not WHETHER. NO-GO / REVISE if dose was not delivered (Metric 1 failed) - in that case the pilot tested nothing, and the design, not the concept, needs fixing first.

Two notes for the board

Lock the exact target numbers AFTER the Week-0 baseline. Promising "+0.5 sub-level" before we know where students start is not responsible; the shapes above guide measurement, the numbers are set once baseline is in.

Every metric is pre/post CHANGE, not proof of cause - except Metric 5 (dose-response), which is the closest this pilot comes to isolating the AI's effect. This is a pilot, framed honestly as one.